## Product Backlog
Priority | User Story | Story Point Estimate
1 | As an ASE Tutor, I want to see a specification of the system to be developed, I want to see any design artifacts (e.g. UML models) produced during the development process.
3 | As a Team Member I want to move User Stories from the Product Backlog to the Sprint Backlog. The User Stories in the Sprint Backlog will represent the requirements for the work that the development team will complete during that Sprint. | 12
4 | As a Team Member, I want to be able to state how much time I have spent working on a task each day, and how much time is remaining to complete the Task. | 12
5 | As a Product Owner, I want to be able to see which User Stories are being worked on in the current Sprint, and what User Stories are left in the Product Backlog. | 12
6 | As a Scrum Master, I want to be able to see which User Stories are being worked on in the current Sprint, and the time spent and remaining on each Task, User Story, and Sprint as a whole. | 12
7 | As a Team Member, I want to be able to add Story Point Estimates to the User Stories in the Product Backlog. | 12
8 | As a Team Member, I want to be able to add estimates to the Tasks in the User Stories in the current Sprint. The estimate will represent the number of hours expected to complete the task. | 12
9 | As a Team Member, I want to be able to move any Tasks remaining at the end of the Sprint either back into the Product Backlog, or onto the next Sprint. This is so that any unfulfilled Tasks can be completed in the next Sprint. | 12
10 | As a Security Manager, I only want logged in Users to see and maintain any of the information in the System. This is so that any sensitive information is only shared within the team | 12
11 | As a System Administrator, I want to be able to add Users to the System and set their logon username and reset their password. | 12
12 | As a Scrum Master, I want to see a Burndown Chart, graphing the accumulated Task estimates distributed evenly throughout the Sprint, against the accumulated time remaining on all tasks, as the Sprint progresses. This is so that I can see if the Scrum is on target, and can report this information in the Scrum of Scrums each day. | 12
13 | As a Security Manager, I want any changes made to be auditable and linked to the User that made the change. This is so that there is an audit trail of changes linked to a specific person. | 12
14 | As an ASE Tutor, I want to see the source code for the product itself. I want the JUnit test code used during development of the product. Once added as a project to the Eclipse IDE the source should easily compile and be testable. | 12
15 | As an ASE Tutor, I want to see a Demo of the working system.
16 | As a Product Owner, I want to be able to order User Stories in the Product Backlog by a priority that I choose. | 12

## Sprint 5 Backlog
User Story | Task no. | Task | Assigned To | Status | Remaining (hours) | Estimate (hours)
User Story Details
|  | UI | Bamo | Complete | 0 | 6
Task Details
|  | UI | Bamo | Complete | 0 | 6
Login
|  | UI | Stuart | Complete | 0 | 6
Product Backlog Lister
|  | UI | Stuart | Complete | 0 | 6
Sprint Backlog Details
|  | UI | Fran | Complete | 0 | 6
Product BackLog Details
|  | UI | Fran | Complete | 0 | 6
[5 empty] | 0 | 36

## Sprint 4 Backlog
User Story | Task no. | Task | Assigned To | Status | Remaining (hours) | Estimate (hours)
As a Product Owner, I want to create a Product Backlog . |  |  |  |  | 1 | 1
| 1.1 | JUnit Tests | Stuart | Assigned
[5 empty] | 0 | 1
As a Team Member, I want to be able to assign a Task to myself to work on. AOnce Task is completed, I want to be able to close the Task so no-one else can work on it, and have a visible indicator that this Task is complete.
| 2.1 | Assign Task to User (TeamMember) | Fran | Assigned
| 2.2 | Add DB Access Code for User classes | Fran | Assigned | 0 | 6
| 2.3 | Add behaviour diagram | Stuart | In Progress
As a Product Owner, I want to be able to add User Stories with descriptions to the Product Backlog. |  |  |  |  | 0 | 3
| 3.1 | Create method to add User Story to ProductBacklog | Bamo | Assigned | 0 | 3
[5 empty] | 0 | 3
[5 empty] | 0 | 3
[5 empty] | 3 | 3
As a Team Member I want to move User Stories from the Product Backlog to the Sprint Backlog. The User Stories in the Sprint Backlog will represent the requirements for the work that the development team will complete during that Sprint. |  |  |  |  | 3 | 3
[5 empty] | 3 | 3
As a Team Member, I want to be able to state how much time I have spent working on a task each day, and how much time is remaining to complete the Task. |  |  |  |  | 3 | 3
[5 empty] | 0 | 6
As a Product Owner, I want to be able to see which User Stories are being worked on in the current Sprint, and what User Stories are left in the Product Backlog.
[5 empty] | 13 | 38

## Sprint 3 Backlog
User Story | Task no. | Task | Assigned To | Status | Remaining (hours) | Estimate (hours)
As an ASE Tutor, I want to see a specification of the system to be developed, I want to see any design artifacts (e.g. UML models) produced during the development process.
| 1.1 | - Add Use Case Diagram file to SVN | Bamo | Complete | 1 | 1
| 0.1 | Add script for all DB tables | Fran | Complete | 0 | 1
As a Product Owner, I want to create a Product Backlog .
| 2.1 | - Code (and JUnit Tests +Mock Objects) for Project.createProductBacklog | Stuart | Complete | 0 | 6
As a Team Member, I want to be able to add Tasks with descriptions to the User Stories in the current Sprint Backlog. The Tasks will represent the units of work that will be completed by the development team to fulfil that User Story.
| 3.1 | Add Tasks class | Bamo | Complete | 0 | 3
| 3.2 | Associate Task with User Story | Bamo | Complete | 0 | 3
| 3.3 | Add DB Access code | Bamo | Complete | 0 | 3
| 3.4 | Add Behaviour diagram | Stuart | Complete | 0 | 3
As a Team Member, I want to be able to assign a Task to myself to work on. AOnce Task is completed, I want to be able to close the Task so no-one else can work on it, and have a visible indicator that this Task is complete.
| 4.1 | Add User class and subclasses | Fran | Complete | 3 | 3
| 4.2 | Assign Task to User (TeamMember) | Fran | Assigned | 3 | 3
| 4.3 | Add DB Access Code for User classes | Fran | Assigned | 3 | 3
| 4.4 | Add behaviour diagram | Stuart | In Progress | 3 | 3
As a Product Owner, I want to be able to add User Stories with descriptions to the Product Backlog.
| 5.1 | Create method to add User Story to ProductBacklog | Bamo | Assigned | 0 | 6
[5 empty] | 13 | 38

## Sprint 2 Backlog
User Story | Task no. | Task | Assigned To | Status | Remaining (hours) | Estimate (hours)
As an ASE Tutor, I want to see a specification of the system to be developed, I want to see any design artifacts (e.g. UML models) produced during the development process.
| 1.1 | - Add Use Case Diagram file to SVN | Bamo | Carried Over | 1 | 1
| 1.2 | - Look at adding Hibernate to SVN | Fran | Complete | 0 | 3
| 1.3 | - Add component diagram to SVN | Stuart | Complete | 0 | 1
As a Product Owner, I want to create a Product Backlog .
| 2.1 | - Code (and JUnit Tests +Mock Objects) for Project.createProductBacklog | Stuart | Carried Over | 6 | 6
| 2.2 | - Create DB side | Fran | Complete | 0 | 1
As a Product Owner, I want to be able to add User Stories with descriptions to the Product Backlog.
| 3.1 | - code (and JUnit + Mock Objects) for creating User Stories | Bamo | compeleted | 0 | 6
| 3.1 | - DB Side |  |  | 1 | 1
As a Team Member, I want to create a Sprint Backlog with a start and end date for the Sprint
| 4.1 | - code (and JUnit + MockObjects )for creating Sprint backlog | Fran | Complete | 0 | 6
| 4.2 | - DB Side | Fran | Complete | 0 | 1
[5 empty] | 7 | 21
Note on E1: Not Started, Assigned, In Progress, Complete, Carried Over -Frances Vaughan

## Sprint 1 Backlog
User Story | Task no. | Task | Assigned To | Status | Remaining (hours) | Estimate (hours)
As an ASE Tutor, I want to see a specification of the system to be developed, I want to see any design artifacts (e.g. UML models) produced during the development process.
| 1.1 | - Add class diagram to Visual Paradigm | Bamo | Complete | 0 | 3
| 1.2 | - Add class diagram (image) to SVN | Bamo | Complete | 0 | 1
| 1.3 | - Add Use Case Diagram file to SVN | Bamo | Carried Over | 1 | 1
| 1.4 | - Add DB ER diagram to visual paradigm | Fran | Complete | 0 | 3
| 1.5 | - Look at adding Hibernate to SVN | Fran | Carried Over | 3 | 3
| 1.6 | - Add component diagram to Visual paradigm | Stuart | Complete | 0 | 3
| 1.7 | - Add component diagram to SVN | Stuart | Carried Over | 1 | 1
As a Product Owner, I want to create a Product Backlog .
| 2.1 | - Create (all) Classes from Visual Paradigm | Bamo | Complete | 0 | 1
| 2.2 | - Create (all) model stub classes in SVN | Bamo | Complete | 0 | 1
| 2.3 | - Code (and JUnit Tests +Mock Objects) for Project.createProductBacklog |  | Carried Over | 6 | 6
| 2.4 | - Create DB side | Fran | Carried Over | 1 | 1
As a Product Owner, I want to be able to add User Stories with descriptions to the Product Backlog.
| 3.1 | - sequence/activity diagram for creating user stories | Stuart | Complete | 0 | 3
| 3.2 | - code (and JUnit + Mock Objects) for creating User Stories |  | Carried Over | 6 | 6
| 3.3 | - DB Side |  | Carried Over | 1 | 1
[5 empty] | 18 | 29